## Project 1
|  | Jun |  |  |  | July |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov
Activities | Resources | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Project Start | Project Manager
Gather requirements | Business Analyst | bar: Jun 1 to Jun 3
Design | Engineer 1 | bar: Jun 4 to July 2
Review | Project Manager | bar: July 3
Design signed off - Milestone | Project Manager
Build Prototype | Engineer 1 | bar: July 4 to Aug 1
Test Prototype in factory | Test Lead | bar: Aug 2
Ship Prototype | Project Manager | bar: Aug 2
Prototype arrives on site | Project Manager | bar: Aug 2
Test Prototype on site | Test Lead | bar: Aug 2 to Aug 3
Run Protyotype compliance | Compliance Manager | bar: Aug 3 to Sep 2
Demo prototype to Execs | Engineer 1, PM | bar: Sep 1 to Sep 2
Exec Review of prototype | Project Manager | bar: Sep 3
Exec Sign off prototype | Project Manager
Mass production of product | Production Team | bar: Sep 4 to Oct 3
Launch Product | Sponsor
Closure report | Project Manager | bar: Oct 4 to Nov 1
Project Close | Project Manager

## Sheet1
Task Mode | Task Name | Duration | Start | Finish | RAG | Predecessors | Milestone | Resource Names | Comentary
Auto Scheduled | Project Start | 0 days | Sat 01/06/24 | Sat 01/06/24 |  |  | Yes | Project Manager
Auto Scheduled | Gather requirements | 5 days | Mon 03/06/24 | Fri 07/06/24 |  | 1 | No | Business Analyst
Auto Scheduled | Design | 5 days | Mon 10/06/24 | Fri 14/06/24 |  | 2 | No | Engineer 1
Auto Scheduled | Review | 5 days | Mon 17/06/24 | Fri 21/06/24 |  | 3 | No | Project Manager
Auto Scheduled | Design signed off - Milestone | 0 days | Fri 21/06/24 | Fri 21/06/24 |  | 4 | Yes | Project Manager
Auto Scheduled | Build Prototype | 10 days | Mon 24/06/24 | Fri 05/07/24 |  | 5 | No | Engineer 1
Auto Scheduled | Test Prototype in factory | 5 days | Mon 08/07/24 | Fri 12/07/24 |  | 6 | No | Test Lead
Auto Scheduled | Ship Prototype | 2 days | Mon 15/07/24 | Tue 16/07/24 |  | 7 | No | Project Manager
Auto Scheduled | Prototype arrives on site | 1 day | Wed 17/07/24 | Wed 17/07/24 |  | 8 | No | Project Manager
Auto Scheduled | Test Prototype on site | 5 days | Thu 18/07/24 | Wed 24/07/24 |  | 9 | No | Test Lead
Auto Scheduled | Run Protyotype compliance | 20 days | Thu 25/07/24 | Wed 21/08/24 |  | 10 | No | Compliance Manager
Auto Scheduled | Demo prototype to Execs | 1 day | Thu 22/08/24 | Thu 22/08/24 |  | 11 | No | Engineer 1,PM
Auto Scheduled | Exec Review of prototype | 5 days | Fri 23/08/24 | Thu 29/08/24 |  | 12 | No | Project Manager
Auto Scheduled | Exec Sign off prototype | 0 days | Thu 29/08/24 | Thu 29/08/24 |  | 13 | Yes | Project Manager
Auto Scheduled | Mass production of product | 30 days | Fri 30/08/24 | Thu 10/10/24 |  | 14 | No | Production Team
Auto Scheduled | Launch Product | 0 days | Thu 10/10/24 | Thu 10/10/24 |  | 15 | Yes | Sponsor
Auto Scheduled | Closure report | 10 days | Fri 11/10/24 | Thu 24/10/24 |  | 16 | No | Project Manager
Auto Scheduled | Project Close | 0 days | Thu 24/10/24 | Thu 24/10/24 |  | 17 | Yes | Project Manager

## Project 2
Jan
Activities | Resources | 1 | 2 | 3 | 4
Foundation
Excavation
Footers
Concrete
Interior
Wall
Floor
Tiles
Utility Instalation
Appliances
Electrical
Plumbing